## 工作表1
Risk Checklist
Risk Description | Class | X | L | W | C | S
The requirements defined in the software requirement analysis are not clear, and further definition will expand the scope of the project; after the software development reaches a certain stage, A suddenly needs to change the demand. | Demand risk | 1 | 1 | 1 | 1 | 1 | 5
Product size (number of code lines, function points, etc.) is greater than estimated, increasing development time, delaying progress | Planning risk |  | 1 |  |  |  | 1
Not familiar with the product area of equipment rental software, spending more time on design and implementation than expected |  |  | 1 | 1 |  |  | 2
After the software development reaches a certain stage, the project budget is cut due to management decision-making or external emergencies. The original project plan is blocked due to limited funds, and major adjustments are required. | Organizing Risk | 1 | 1 | 1 | 1 | 1 | 5
Poor communication between members of the software development team and ineffective collaboration | Staff Risk | 1 | 1 | 1 |  | 1 | 4
The software development team lacks the necessary capabilities and quality, affecting the development schedule and product quality |  |  |  |  | 1 |  | 1
The loss of core personnel during the project development process led to the stagnation of the project. The company was unable to recruit new workers who could perform the core tasks in a short period of time, and the customer had a definite deadline for the completion of the project. As a result, the company’s reputation was damaged. |  | 1 | 1 | 1 | 1 |  | 4
Development tools are not as effective as expected, developers need time to create work environment or switch new tools | Development environment risk | 1 |  |  |  |  | 1
There are unhandled deficiencies in the IDE used for software development and maintenance, resulting in stagnation of the development process | [5 empty] | 1 | 1
Separately developed modules cannot be effectively integrated and need to be redesigned or produced | Design and Implementation Risk | 1 |  | 1 |  | 1 | 3
Designed algorithms are inefficient and affect software performance |  |  |  |  | 1 |  | 1
The customer did not or could not participate in the review of the planning, prototype and specification stages, resulting in unstable demand and changes in the product production cycle | Client Risk |  |  | 1 |  |  | 1
The time of the customer's response (such as answering or clarifying the time related to the requirement) is longer than expected |  | 1 |  |  |  |  | 1
Customers are dissatisfied with the final deliverables and require redesign and redo |  | 1 | 1 | 1 | 1 | 1 | 5
Correcting unacceptable products of poor quality, Need more testing, design, and implementation work than expected, extending the development cycle | Product Risk | 1 |  | 1 | 1 |  | 3
Develop additional unneeded features to extend the schedule
To strictly ensure software compatibility, more testing, design, and implementation work than expected
Excessive document writing leads to slower than expected development | Process Risk |  | 1 |  | 1 | 1 | 3
No good architecture, lack of good development specifications, causing conflicts between modules | Technical Risk
Inconsistent database and server performance causes the system unable to withstand short-term high-traffic access, eventually crashing the system |  | 1 |  | 1 | 1 | 1 | 4
Sudden occurrences such as power outages, or hardware equipment due to disasters (fires, earthquakes, etc.) Which leads to data loss in the database |  | 1 | 1 | 1 |  | 1 | 4
Insufficient database security performance, causing customer privacy leaks or system crashes when hacking |  |  | 1 | 1 | 1 | 1 | 4
Inadequate software security, the encryption of important information is too simple and easy to be externally exploited |  |  | 1 | 1 | 1 |  | 3
There is no obvious error found in the functional test phase program, causing loss after the program is released | Software testing risk | 1 | 1 |  |  | 1 | 3
The contract between the leasing company and the project developer cannot define the responsibilities and obligations of both parties, and there are disagreements in the development process. | Contract Risk | 1 | 1 |  | 1 |  | 3
The code is not high quality, poor readability, difficult to maintain | Software Maintenance Risk | 1 |  | 1 | 1 | 1 | 4
Low code reusability and scalability do not facilitate the expansion of new features |  | 1 | 1 | 1 |  | 1 | 4
When the software is running, the loading speed is slow and the stability is poor. | Software Use Risk |  |  |  |  | 1 | 1
The software does not have detailed tutorials, resulting in errors in the use of software by related personnel |  |  |  |  | 1 |  | 1
Poor interactivity in interface design makes it difficult for users to use |  |  | 1 |  | 1 | 1 | 3
|  | 15 | 15 | 15 | 15 | 15