## Sheet1
Risk Management Worksheet
No. | Risk Name | Type of Risk | Trigger | Description of the Risk | Probability of the Risk ( 1 to 10 ) | Impact of the Risk ( 1 to 10 ) | Severity of the Risk | Description of the Severity | Risk planning | Outcome value
R1 | Changing or Unclear Software Requirements | Demand risk | At the stage of software requirement analysis, the participation degree of Party A is not enough; the requirement of software is vague, the quality assurance of requirement specification is not enough. | The requirements defined for software requirements analysis are not clear, and further definitions will extend the scope of the project; after a certain stage of software development, Party A suddenly demands changes in demand. | 6 | 8 | 48 | High | After consultation with customers, implement requirements change or redefine requirements, while strengthening demand management and quality review. | -43.5k
R2 | Budget Cutting | Organizing Risk | When making the software project plan, the actual situation is not fully investigated, and the budget is too optimistic. Management temporarily decided to take part of the project budget to give priority to other major and urgent project needs. The company's revenue is reduced and its funds are scarce, so it can not support the original budget of the project. | After the development of software to a certain stage, due to management decision or external emergencies and other causes of project budget reduction, the original project plan is blocked due to limited funds and need to make a major adjustment. | 3 | 6 | 18 | Low | According to the reduction of the budget, the project plan is reformulated and implemented. | -31k
R3 | Poor Teamwork | Staff Risk | Conflicts between software development team members are not good. Team members have poor communication skills, lack of experience in collaborative development, and no in-house training. | Communication between software development team members is not good enough to cooperate effectively. | 7 | 7 | 49 | High | The company conducts training on staff communication skills and teamwork, organizing group building activities to increase tacit agreement between team members. | -17k
R4 | Loss of Core Software Developers | Staff Risk | The core members are cut off by the competitors or leave for private reasons; the core members of the project group and the development team have irreconcilable contradictions and decide to leave the team because of the problem of the allocation of salary or the uneven distribution of tasks. | In the process of project development, the core staff is lost, the project is stagnated, and the company can not recruit the staff for the core task in a short time, and the customer has a clear time limit for the completion of the project, and the company's reputation is damaged. | 3 | 7 | 21 | Relative Low | Strengthen team construction and improve welfare treatment | -26k
R5 | Difficult to Integrate All Modules | Design and Implementation Risk | In the process of project development, each component of the team does not pay attention to communication and communication, and does not use a unified software development model. The interface specification is not clearly defined or even has no interface. | The modules developed separately can not be effectively integrated, so they need to be redesigned and implemented. | 4 | 7 | 28 | Relative Low | Redesign the interface with the goal of smooth docking of components. | -32k
R6 | Customer Request to Redo the Project | Client Risk | There is a failure to communicate effectively between customers and development teams. | The customer is not satisfied with the final delivered product, and asks to repeat it. | 2 | 10 | 20 | Low | Restart the project with the original project as a reference | -59k
R7 | Progress Delay Caused by Correcting Products | Product Risk | Some developers are limited in technology level, and the products developed can not meet the needs. | Correcting unacceptable products with low quality requires more testing, design and implementation work than expected, extending the development cycle. | 5 | 5 | 25 | Relative Low | Hire higher level developers | 3.5k
R8 | Documents Overwriting | Process Risk | The detailed documentation of customer requirements indicates that the time required for writing documents is not accurately predicted in project planning, and the ability of developers to write documents is also insufficient. | Excessive documentation leads to a longer development process than expected. | 1 | 3 | 3 | Extremely Low | Delay the date of submission and focus on the quality of the document | 1k
R9 | Low Concurrent Performance of the System | Technical Risk | The developer can not accurately predict the peak value of the system, and can not guarantee the system's concurrent performance or multi thread processing capability, which makes the system's pressure bearing capacity low. | The concurrent performance of database and server is insufficient, resulting in the system unable to endure short time and large flow access. | 9 | 9 | 81 | Extremely High | Pay attention to the high concurrent performance of the database during development | 18k
R10 | Data Loss Caused by Emergencies | Technical Risk | The database lacks backup and the necessary recovery mechanism. | Emergencies such as power outage, or hardware damage caused by disaster (fire, earthquake, etc.) or other causes, cause data loss in the database. | 1 | 10 | 10 | Extremely Low | Complete backup of data in multiple regions | -36.5k
R11 | Information Disclosure Caused by a Lack of System Security | Technical Risk | There is a problem in the configuration of database rights, or the password of the database user account is too simple. The encryption algorithm of the network transmission data is too simple, and there are loopholes in the front end software or the server software. | The security performance of the database is insufficient, which causes the customer privacy disclosure or the system collapse when the hacker attacks; the software security is insufficient, the important information encryption means are too simple and easy to be cracked by the outside. | 4 | 8 | 32 | Relative Low | Set aside the extra development time for system security | -21.5k
R12 | Overabundance of Software Defects after Release | Test Risk | The test staff is not good enough or the testing technology is insufficient, the test case design is incomplete, and there is no complete coverage of the business path. | In the functional testing stage, there are obvious defects that are not found, resulting in loss after the release of the program. | 5 | 7 | 35 | Relative Low | Hire a higher level software testing engineer. | -18.5k
R13 | Contract Loopholes | Contract Risk | There is no legal adviser. The contracts signed by both parties do not specify the boundary of the project and the responsibilities of both parties. | The responsibilities and obligations of the two parties are not clear, and disputes arise during the development process. | 2 | 6 | 12 | Low | Look for legal technical advisors before negotiating contracts. | -5k
R14 | Difficult to maintain and extend software | Software Maintenance Risk | There is no uniform code compilation standard, and the functional modules designed are highly coupled. | Code readability and scalability are not good enough for developers to maintain the software and extend new functions. | 8 | 7 | 56 | High | Formulate code writing specification | -25k
R15 | Unreasonable Interface Interaction Design | Software Use Risk | Lack of user participation in the development and testing process, developers do not fully consider user experience. | Poor interface interactivity make it inconvenient for users to use the software | 2 | 4 | 8 | Extremely Low | Invite users to experience prototypes | 0.5k